## Sheet1
Validify UI Screen Status
Entity | Screen | Action Item# | Action Item Description | Responsible | Status | Due Date | Completed Date | Comments
All | Login | 1 | Provide Suraj with new tempory logo (provided by Adam) | Don | Done | 2017-07-29 | 2017-07-29
|  | 2 | Insert new temporary logo | Suraj | Done
|  | 3 | Remove "Contact" and phone number from bottom of page | Suraj | Open
|  | 4 | Remove 'Validify all rights reserved" at bottom of page; yes this is a new request. | Suraj | Open
|  | 5 | Provide public search UI behavior for log in page area | Don | Open
|  | 6 | Split into 2 sections. 1 The nomral Validify user login. 2 A section for public record search (Don to provide functionlaity) | Suraj | Open
| All | 1 | Remove Validify from top left of UI's (remove Validify branding on all pages except login) | Suraj | Open
|  | 2 | Make Left menu column go all the way to top of page | Suraj | Open
|  | 3 | Move the 3 dash lines (hamburger) to the far left just above the side menu icons | Suraj | Open
|  | 4 | Have Search box at top right of all UI's. Also have the word 'Search" within the seach box. As user begins typing in the search box start showing all matches in a pop up box below that matches regardless of Entity. From there the user can click on the specific item from a the pop up. | Suraj | Open
|  | 5 | Any UI that displays a table/detail listing of data, highlite the column that is being sorted | Sura | Open
|  | 6 | Anywhere a status is shown add "Since" in the column header. Since represents the date the status occurred. Always show the word 'ACTIVE" in green and "SUSPENDED" in red. In the colummn details show the status and directly below the stats show the date that status occured.
|  | 7 | Provide UI behavior for data in pop up screen resulting from upper right search box for all screens | Don | Open
|  | 8 | Remove separate columns dealing with ACTIVE or SUSPENDED in regards to change the status. Allow user to click on the actual status field (ACTIVE or SUSPENDED) which then shows the details on that entiry including suspension history. If the current status is "ACTIVE" then prompt user 'Suspend?". If the current status is "SUSPENDED" then prompt user "Reactivate?". | Suraj | Open
|  | 9 | All landing pages from a user login will be title 'Home Page" not "Dashboard" | Suraj | Open
|  | 10 | At the top of the left menu on all screens Show the Entity Name and directly below show the user name | Suraj | Open
|  | 11 | User a better font. Will explain in person | Suraj | Open
|  | 12 | Ledft menu: Remove Icons, Heading of section ALL CAPS and a slight gray color, detail actions (UI's) listed under the heading should be white and lower case | Suraj | Open
|  | 13 | the line separate the section obove the content on the left shouw have no showdow but a clean subtle line | Suraj | Open
DOI | Home Page | 1 | Remove graphics from pods | Suraj | Done
|  | 2 | Simplify verbage in the top 3 pods to: "Liabilities", Forfeitures" & "Unpaid Judgements" | Suraj | Done
|  | 3 | Round the $ in the top 3 pods; ex: 5.2B or 1.2M or 125.3k | Suraj | Done
|  | 4 | On Top 3 Pods change "Number of Bonds" to '# Bonds" and center under the above headings within the POD. | Surja | Open
|  | 5 | Consolidate the bottom 3 Suspension pods into 1 pod (make it the 4th pod across the page). Once use clicks on this pod display 4 buttons : "Surreties" "Agencies" "Agents" and "All". Show the cooresponding list table depending on which entiry selected. If user selects all the show all the tables in the bottom area of the screen. | Suraj | Open |  |  | Needs to look better
|  | 6 | Make the pods a little smaller
| Home Page / Liabilities | 1 | When click on Liabilities, must prompt for which entity Liabilities to be shown: 'Sureties" Agencies" or "Agents" | Suraj | Open
|  | 2 | Once you choose which entity ttype hen show the selected entity type in the first 2 columns not all three. Only show one of the entiy types "Sureties", "Agencies" or "Agents". | Suraj | Open
| Home Page / Forfeitures | 1 | When click on Forfeitures, must prompt for which entity Liabilities to be shown: 'Sureties" Agencies" or "Agents" | Suraj | Open
|  | 2 | Once you choose which entity ttype hen show the selected entity type in the first 2 columns not all three. Only show one of the entiy types "Sureties", "Agencies" or "Agents". | Suraj | Open
| Home Page / Judgements Unpaid | 1 | When click on Judgements Unpaid, must prompt for which entity Liabilities to be shown: 'Sureties" Agencies" or "Agents" | Suraj | Open
|  | 2 | Once you choose which entity ttype hen show the selected entity type in the first 2 columns not all three. Only show one of the entiy types "Sureties", "Agencies" or "Agents". | Suraj | Open
Surety | Home Page | 1 | Simplify verbage in the top 3 pods to: "Liabilities", Forfeitures" & "Unpaid Judgements" | Suraj | Open
|  | 2 | Add a new first POD "Bond Increase Request". Like the other pod show the # Bonds below the title. If 0 then make the 0 green (bold), if 1 or more make the number red (bold)
|  | 3 | Add "Inventory Remaining" POD after Unpaid Judgements | Suraj | Open
|  | 4 | On Top 3 Pods change "Number of Bonds" to '# Bonds" and center under the above headings within the POD. | Surja | Open
|  | 5 | Make the pods a little smaller |  | Open
|  | 6 | Add a new pod for 'Suspensions" similar to DOI Home Page Suspension. Thid pod woll only deal with Agencies and Agents. If user clicks on one of the suspension options show the detail table of data exactly like the table under DOI Home Page Suspension results | Suraj | Open
|  | 7 | Change the order of the left menu to Agencies, Agents then Bonds | Suraj | Open
|  | 8 | Pod Order - Top row: Bond Increase Request, Inventory Remaining, Suspensions 2nd Row: Liabilities, Forfeitures, Unpaid Judgements | Suraj | Open
| Liabilities / Agency Details |  | Remove 'Regulate" | Suraj | Open
|  |  | DOI Status is either "ACTIVE" (bold green) or 'SUSPENDED" (bold red). Surety user cannot change this status | Suraj | Open
|  |  | For the status dates on this screen directly left (as it is now) show "Since" then the latest status date | Suraj | Open
|  |  | Surety Status is either "ACTIVE" (bold green) or 'SUSPENDED" (bold red). If Surety user clicks on the Surety status, wllow user to change the status. See item #8 under All Entiry and All screens | Suraj | Open
| Forfeitures / Agency Details |  | Remove 'Regulate" | Suraj | Open
|  |  | DOI Status is either "ACTIVE" (bold green) or 'SUSPENDED" (bold red). Surety user cannot change this status | Suraj | Open
|  |  | For the status dates on this screen directly left (as it is now) show "Since" then the latest status date | Suraj | Open
|  |  | Surety Status is either "ACTIVE" (bold green) or 'SUSPENDED" (bold red). If Surety user clicks on the Surety status, wllow user to change the status. See item #8 under All Entiry and All screens | Suraj | Open
| Unpaid Judgements / Agency Details |  | Remove 'Regulate" | Suraj | Open
|  |  | DOI Status is either "ACTIVE" (bold green) or 'SUSPENDED" (bold red). Surety user cannot change this status | Suraj | Open
|  |  | For the status dates on this screen directly left (as it is now) show "Since" then the latest status date | Suraj | Open
|  |  | Surety Status is either "ACTIVE" (bold green) or 'SUSPENDED" (bold red). If Surety user clicks on the Surety status, wllow user to change the status. See item #8 under All Entiry and All screens | Suraj | Open
| Inventory Remaining / Agency Details |  | For this new pod same behavior as one of the existing. When click on this pod Show Agency Name, Total Inventory, Inventory Remaining | Suraj | Open