## Action Items
Validify UI Screen Status - As of 09/25/17
Entity | Screen | Action Item# | Action Item Description | Responsible | Status | Due Date | Completed Date | Comments
All | Login | 1 | Provide Suraj with new tempory logo (provided by Adam) | Don | Done | 2017-07-29 | 2017-07-29
|  | 2 | Insert new temporary logo | Suraj | Done
|  | 3 | Remove "Contact" and phone number from bottom of page | Suraj | Done
|  | 4 | Remove 'Validify all rights reserved" at bottom of page; yes this is a new request. | Suraj | Done
|  | 5 | Provide public search UI behavior for log in page area | Don | Done
|  | 6 | Split into 2 sections. 1 The nomral Validify user login. 2 A section for public record search (Don to provide functionlaity) | Suraj | Done
|  | 7 | Remove Entiry tabs from login section and use an email for each entity login. We want to get the final look of the login ASAP | Suraj | Done
| All | 1 | Remove Validify from top left of UI's (remove Validify branding on all pages except login) | Suraj | Done
|  | 2 | Make Left menu column go all the way to top of page, also related to behavior to item 1 above | Suraj | Done
|  | 3 | Move the hamburger to the far left just above the side menu icons | Suraj | Done
|  | 4 | Have Search box at top right of all UI's. Also have the word 'Search" within the seach box. As user begins typing in the search box start showing all matches in a pop up box below that matches regardless of Entity. From there the user can click on the specific item from a the pop up. | Suraj | Done
|  | 5 | Any UI that displays a table/detail listing of data, highlite the column that is being sorted | Sura | Done |  |  | Currently some are underlined but it would be nice to have the column shadowed/highlighted in a light gray
|  | 7 | Provide UI behavior for data in pop up screen resulting from upper right search box for all screens | Don | Done
|  | 8 | Remove separate columns dealing with ACTIVE or SUSPENDED in regards to change the status. Allow user to click on the actual status field (ACTIVE or SUSPENDED) which then shows the details on that entiry including suspension history. If the current status is "ACTIVE" then prompt user 'Suspend?". If the current status is "SUSPENDED" then prompt user "Reactivate?". | Suraj | Done
|  | 9 | All landing pages from a user login will be title 'Home Page" not "Dashboard" | Suraj | Done
|  | 10 | At the top of the left menu on all screens Show the Entity Name and directly below show the user name. This needs to be in the purple section directly above the lef bar menu. 08/22/17: Make the entiry font size only slightly bigger than user name. | Suraj | Done
|  | 11 | User a better font. Will explain in person | Suraj | HOLD |  |  | skip this one for now, but need thoughts on a nice font style and size etc.
|  | 12 | Ledft menu: Remove Icons, Heading of section ALL CAPS and a slight gray color, detail actions (UI's) listed under the heading should be white and lower case | Suraj | Done
|  | 13 | the line separating the section obove the content should have no showdow but a clean subtle line | Suraj | Done
|  | 14 | Change "Validify User Login" to "User Login" | Suraj | Done
|  | 15 | Change "Public Search" to "Public Bond Search" | Suraj | Done
|  | 16 | Put a diagonal line down the login page to separate the User Login and the Public Search side. Figure out the best way since the Validify Logo is centered and we of course do not want this line going through the logo. Open to ideas | Suraj | Done
|  | 17 | Ensure all UI pages have the page identified in the upper section of the UI over the content (not over the left menu). Mus be consistent best exmple is "AGENCIES / bond an agency". The first part of the screen name is in CAPS (same as header in left menu) and the specific screen is in lower case (same as indented sections of the left menu) | Suraj | Done
|  | 18 | On all UI's that allow user to changea field, or submit a bond etc., there shoud be prompt that is either "Save" or "Are you sure?". Another example, when a user clicks on a status ACTIVE or SUSPENDED to change the status there should be a "SAVE" buttong or "Are you sure" | Suraj | Done
|  | 10 | Correction to menu, hamburger, UI name etc. behvior. Top left of lef bar menu should have entiry name and directly under that the user name. The hamburger should be just right of the left bar menu (in the white section). On the same top row as the hamburger the UI name should show. 08/22/17 When clcik on hambuger left menu expandes which is good, HOWEVER, when you compress the menu the purple section at the very top SHOULD NOT REMAIN OVER INTO THE WHITE SECTION. THE COMPRESSED LEFT MENU SHOULD REMAIN THE NARROW WIDTH ALL THE WAY TO THE TOP. | Suraj | Done
|  | 11 | Change all references of 'Bond #" to "Power #" throughout system | Suraj | Done
|  | 10 | On All table/list of detailed data, bold the column heading with n underline. Or a better idea to separate the heading from the detail data better. | Suraj | Done
|  | 11 | Lets choose a consistent Update or Save button throughout. Lets go with "Save" | Suraj | Done
|  | 12 | Also, even now for demo purposes if we don’t hit save then make sure the data stay as it was
|  | 13 | When clicking on a column table header to change a sort, the new column beining sorted on should now be shaded
|  | 14 | Make default left menu o be open, even on initial login to Home Page. Let the user click the hanburger if they want to close it
DOI | Home Page | 1 | Remove graphics from the info graphics/pods | Suraj | Done
|  | 2 | Simplify verbage in the top 3 pods to: "Liabilities", Forfeitures" & "Unpaid Judgements" | Suraj | Done
|  | 3 | Round the $ in the top 3 info graphics; ex: 5.2B or 1.2M or 125.3k | Suraj | Done
|  | 4 | On Top 3 Pods change "Number of Bonds" to '# Bonds" and center under the above headings within the POD. | Surja | Done
|  | 5 | Consolidate the bottom 3 Suspension pods into 1 pod (make it the 4th pod across the page). Once use clicks on this pod display 4 buttons : "Surreties" "Agencies" "Agents" and "All". Show the cooresponding list table depending on which entiry selected. If user selects all the show all the tables in the bottom area of the screen. | Suraj | Done |  |  | Pop up behaviord should be same as other 3 pods
|  | 6 | Make the info graphics/pods a little smaller | Suraj | Done
|  | 7 | Missing the Suspensions info graphic/pod | Suraj | Done
|  | 8 | The left menu order should be Sureties, Agencies then Agents | Suraj | Done
|  | 9 | Home Pgae should just say "Home" not "Home Page: DOI" | Suraj | Done
| ALL | 1 | Each page should show the name of each page. If in Liabilities from Home Page it shoud be "Home-Liabilities" | Suraj | Done |  |  | Same as Surety Ui's
| Home Page / Liabilities | 1 | When click on Liabilities, must prompt for which entity Liabilities to be shown: 'Sureties" Agencies" or "Agents" | Suraj | Done
|  | 2 | Once you choose which entity type then show the selected entity type in the first 2 columns. Only show one of the entiy types "Sureties", "Agencies" or "Agents". | Suraj | Done
|  | 3 | Add last column 'Total Liabilities" | Suraj | Done
| Home Page / Forfeitures | 1 | When click on Forfeitures, must prompt for which entity Liabilities to be shown: 'Sureties" Agencies" or "Agents" | Suraj | Done
|  | 2 | Once you choose which entity ttype hen show the selected entity type in the first 2 columns. Only show one of the entiy types "Sureties", "Agencies" or "Agents". | Suraj | Done
| Home Page / Judgements Unpaid | 1 | When click on Judgements Unpaid, must prompt for which entity Liabilities to be shown: 'Sureties" Agencies" or "Agents" | Suraj | Done
|  | 2 | Once you choose which entity ttype hen show the selected entity type in the first 2 columns. Only show one of the entiy types "Sureties", "Agencies" or "Agents". | Suraj | Done
| Home Page / Suspensions | 1 | When click on suspensions, must prompt for which entity Liabilities to be shown: 'Sureties" Agencies" or "Agents" | Suraj | Done |  |  | Ensure behavior is same as other 3. The order should be Sueties, Agencies then Agents
|  | 2 | Once you choose which entity ttype hen show the selected entity type in the first 2 columns. Only show one of the entiy types "Sureties", "Agencies" or "Agents" or "ALL". 9/11/17 Still need "ALL" option | Suraj | Done |  |  | If choose all we should hve 3 tables listed with the heder of the exntiry (ex. Sureties) to identify the related content of each listing
| SURETIES, AGENCIES, AGENTS | 1 | When you clcik on the left bar menu for either Sureties, Agencies or Agents remove what now shows up after the info graphcs and add the lookup section as shown in excel example. This allows the DOI to regulate the particular entity (Surety, Agency or Agent). | Suraj | Done |  |  | See behavior as shown in AGENCIES / Regulate
|  | 2 | For all 3 of these screens make sure the DOI SUSPENDED info graphics is the same size as the other info graphics. Currently it is bigger. | Suraj | Done
| LEFT MENU | 1 | When I clcik on AGENTS the SURETIES menu item goes to lower case (should stay uppecase) | Suraj | Done
Surety | Home Page | 1 | Simplify verbage in the top 3 pods to: "Liabilities", Forfeitures" & "Unpaid Judgements" | Suraj | Done
|  | 2 | Add a new first info graphic "Bond Increase Request". Like the other info graphics show the # Bonds below the title. If 0 then make the 0 green (bold), if 1 or more make the number red (bold) | Suraj | Done
|  | 3 | Add "Inventory Remaining" info graphic after Unpaid Judgements | Suraj | Done
|  | 4 | On Top 3 Pods change "Number of Bonds" to '# Bonds" and center under the above headings within the POD. | Surja | Done
|  | 5 | Make the pods a little smaller |  | Done
|  | 6 | Add a new pod for 'Suspensions" similar to DOI Home Page Suspension. Thid pod woll only deal with Agencies and Agents. If user clicks on one of the suspension options show the detail table of data exactly like the table under DOI Home Page Suspension results | Suraj | Done
|  | 7 | Change the order of the left menu to Agencies, Agents then Bonds | Suraj | Done
|  | 8 | Pod Order - Top row: Bond Increase Request, Inventory Remaining, Suspensions 2nd Row: Liabilities, Forfeitures, Unpaid Judgements | Suraj | Done
|  | 9 | All Info graphics that prompt for which entiry to view the data should not include a Sureties option as this is the Surety looking at data related to them. | Suraj | Done
|  | 10 | None of the items in the left menu bar are working yet. Thought Solomon created these UI's but may have been overwritten in the last update. | Suraj | Done
|  | 11 | On the default tables that show 'Top 5 Agencies with Highest Forfeiture Amounts - Last 4 Weeks" and the "Top 5 Agents with Highest Forfeiture Amounts - Last 4 Weeks; Make the Header of the table Bold, underline the column headers leave an extra space between the last row of the first table and the header of the next table. Open to ideas to make this look cleaner | Suraj | Done
|  | 12 | For the 2 tables showing top 5 Forfeitures, show 5 rows of data | Suraj | Done
|  | 13 | Page name shows "home page", please show "HOME PAGE"; 8/24/17 Correction make it "HOME" | Suraj | Done
|  | 14 | Always have the left menu OPEN as the default. If the user wants to close the left menu then the user can click on the hamburger | Suraj | Done
| Bond Increase Request/ Details | 1 | When click on this info graphic the detail data columns for Per Bond Limit and Requested Bond Amount should be dollars | Suraj | Done
|  | 2 | Move Approve to far left column and use standard select/approve behavior | Suraj | Done |  |  | maybe ok on right?
|  | 3 | Add last column, after Approve, Called "Decline". I like the update of are you sure. This will apply after all boxes are selected by user. | Suraj | Done |  |  | Still needs the check box section in the actual row.
|  | 4 | Sort detail rows by Agency | Suraj | Done
|  | 5 | The last column "Decline" should also have boxes in the rows for the user to check | Suraj | Done
|  | 6 | Same requirement if you clcik on from Home Page or within the left menu BONDS / increase request: If user clicks on a row then show a pop up of the following detail data: Same detail data when you clcik on a row/line item from AGENCIES / set inventory | Suraj | Done
|  | 7 | Show the amount of request to be greater that Total Inventory remaining and/or greater than per bond limit amount | Suraj | Done
| Liabilities / Agency Details | 1 | Remove 'Regulate" | Suraj | Done
|  | 2 | DOI Status is either "ACTIVE" (bold green) or 'SUSPENDED" (bold red). Surety user cannot change this status | Suraj | Done
|  | 3 | For the status dates on this screen directly left (as it is now) show "Since" then the latest status date | Suraj | Done
|  | 4 | Surety Status is either "ACTIVE" (bold green) or 'SUSPENDED" (bold red). If Surety user clicks on the Surety status, wllow user to change the status. See item #8 under All Entiry and All screens | Suraj | Done
|  | 5 | Column heading should be "Agency Name" Agency License #" NOT "Surety Name" & 'Surety License #" | Suraj | Done
|  | 6 | Missing Surety Staus and Surety Status Since | Suraj | Done
|  | 7 | Screen name should be "HOME / liabilities" | Suraj | Done
|  | 8 | Click on this info graphic, then click on one of the rows you will get to another table with incorrect column headings on the first 2 columns. Should be "Agency" not "Surety" | Suraj | Done
| Forfeitures / Agency Details | 1 | Remove 'Regulate" | Suraj | Done
|  | 2 | DOI Status is either "ACTIVE" (bold green) or 'SUSPENDED" (bold red). Surety user cannot change this status | Suraj | Done
|  | 3 | For the status dates on this screen directly left (as it is now) show "Since" then the latest status date | Suraj | Done
|  | 4 | Surety Status is either "ACTIVE" (bold green) or 'SUSPENDED" (bold red). If Surety user clicks on the Surety status, wllow user to change the status. See item #8 under All Entiry and All screens | Suraj | Done
|  | 5 | Column heading should be "Agency Name" Agency License #" NOT "Surety Name" & 'Surety License #" | Suraj | Done
|  | 6 | Missing Surety Staus and Surety Status Since | Suraj | Done
|  | 7 | Click on this info graphic, then click on one of the rows you will get to another table with incorrect column headings on the first 2 columns. Should be "Agency" not "Surety" | Suraj | Done
| Unpaid Judgements / Agency Details | 1 | Remove 'Regulate" | Suraj | Done
|  | 2 | DOI Status is either "ACTIVE" (bold green) or 'SUSPENDED" (bold red). Surety user cannot change this status | Suraj | Done
|  | 3 | For the status dates on this screen directly left (as it is now) show "Since" then the latest status date | Suraj | Done
|  | 4 | Surety Status is either "ACTIVE" (bold green) or 'SUSPENDED" (bold red). If Surety user clicks on the Surety status, wllow user to change the status. See item #8 under All Entiry and All screens | Suraj | Done
|  | 5 | Column heading should be "Agency Name" Agency License #" NOT "Surety Name" & 'Surety License #" | Suraj | Done
|  | 6 | Missing Surety Staus and Surety Status Since | Suraj | Done
|  | 7 | Change head to Home / Summary Judgments Unpaid - Agencies; keep navigation history in UI page name |  | Done
|  | 9 | Click on this info graphic, then click on one of the rows you will get to another table with incorrect column headings on the first 2 columns. Should be "Agency" not "Surety" | Suraj | Done
| Inventory Remaining / Agency Details | 1 | When click on this pod Show Agency Name, Total Inventory, Inventory Remaining. No need to prompr for entiry as total inventory onlhy relates to an agency | Suraj | Done
|  | 2 | add column for total inventory, total remaining, show Surety Status. Surety Status Since, DOI status, DOU Status Since | Suraj | Done
|  | 3 | Change last column header to 'DOI Status Since" | Suraj | Done
| Suspensions | 1 | Remove Sureties as an option. This is a Surety looking at suspensoin of Agencies or Agents | Suraj | Done
|  | 2 | Show # suspended next to each entiry (Agencies & Agents) | Suraj | Done
| Suspensions / Agencies Details | 1 | Add Surety Status, Surety Status Since, after the DOI Status | Suraj | Done
|  | 2 | Change last column to DOI Status Since | Suraj | Done |  |  | This was moved to the left of Surety Status
|  | 3 | Correct Page title to reflect true navigation "Home - Suspensions - Agencies". | Suraj | Done |  |  | Currently says "DOI Suspended Agencies"
|  | 4 | Remove Date of DOI Suspension column. Not needed | Suraj | Done
|  | 5 | Removed Reason Suspended from column in table. NOTE: When clcik on a specific row the detail below the table will show suspension history with the reason/s | Suraj | Done
|  | 6 | Show at least 3 Agencies in Suspended Status and the status history should show a Suspened entry as the last entry. 09/11/17: Make sure the History status (when you click on a line item) shows SUSPENDED as the most recent entry in the History Status since these are entiries in SUSPENDED status. | Suraj | Done
| Suspensions / Agents Details | 1 | Add Surety Status, Surety Status Since, | Suraj | Done
|  | 2 | Change last column to DOI Status Since | Suraj | Done
|  | 3 | Correct Page title to reflect true navigation "Home - Suspensions - Agents" | Suraj | Done
|  | 4 | Remove Date of DOI Suspension column. Not needed | Suraj | Done
|  | 5 | Removed Reason Suspended from column in table. NOTE: When clcik on a specific row the detail below the table will show suspension history with the reason/s | Suraj | Done
|  | 6 | Show at least 3 Agents in Suspended Status and the status history should show a Suspened entry as the last entry. 09/11/17: Make sure the History status (when you click on a line item) shows SUSPENDED as the most recent entry in the History Status since these are entiries in SUSPENDED status. | Suraj | Done |  |  | Currently there is only one line item and it shows ACTIVE (should be SUSPENDED)
| Total Liability / Agencies Detail | 1 | Add Surety Status, Surety Status Since, after DOI Status/since | Suraj | Done
|  | 5 | Column heading should be 'for "Agencies" | Suraj | Done
| Forfeitures / Agencies Details | 1 | Column should say Amount in Forfeiture | Suraj | Done
|  | 2 | Page Title should also say Forfeiture | Suraj | Done
|  | 3 | Set up up standard status columns, show Surety Status, Surety Status Since, DOI Status, DOI Status Since | Suraj | Done
| Unpaid Judgemenst Agencies Details | 1 | Column should say Unpaid Judgements | Suraj | Done
|  | 2 | Page Title should also say Unpaid Judgements | Suraj | Done
|  | 3 | Set up up standard status columns, show Surety Status, Surety Status Since, DOI Status, DOI Status Since | Suraj | Done
| AGENCIES / bond and agency | 1 | Allow user to add a new agency that is not in Validify. Prompt for Agency Name, License #, address, email, phone. Then provide prompt "Create/Bond Agency" | Suraj | Done
|  | 2 | Add State column after Agency Address column (from address) of Agency | Suraj | Done
|  | 3 | If doing a serach with no results then the agency must be added. Create a button that’s say "Create/Bond Agency". Then the bottom of the screen shows the detail data fields to add the Agency as a first time entiry inot Validify. | Suraj | Done
|  | 4 | Initially show the checkboxes unchecked | Suraj | Done
|  | 5 | When clcik on one of the boxes to bond an existing agency, there is no button to "SAVE" | Suraj | Done
| AGENCIES / set inventory | 1 | On lowest detail screen show Status in bold ACTIVE or SUSPENDED | Suraj | Done
| AGENCIES / Suspended Status | 1 | Remove columns: Date of DOI Suspension and Reason Suspended (this will show in the next level detail if you clcik on the row). Same as Home / Agency Suspension show at least 3 lines of exemaples all in SUSPENDED Status. The detailed status history should show thee last entry as SUPENDED | Suraj | Done |  |  | Should look like Home / suspensions
| AGENTS / bond and agent | 1 | Allow user to add a new agent that is not in Validify. Prompt for Agenct Name, License #, address, email, phone. Then provide prompt "Create/Bond Agenct" | Suraj | Done
|  | 2 | Add State column after Agent Address column (from address) of Agent | Suraj | Done
|  | 3 | If doing a serach with no results then the agent must be added. Create a button that’s say "Create/Bond Agent". Then the bottom of the screen shows the detail data fields to add the Agent as a first time entiry inot Validify. | Suraj | Done
|  | 4 | Initially show the checkboxes unchecked | Suraj | Done
| AGENTS / Suspended Status | 1 | Remove columns: Date of DOI Suspension and Reason Suspended (this will show in the next level detail if you clcik on the row). Same as Home / Agency Suspension show at least 3 lines of exemaples all in SUSPENDED Status. The detailed status history should show thee last entry as SUPENDED | Suraj | Done |  |  | Should look like Home / suspensions
| BONDS / increase request | 1 | Add prompt to 'Save" or 'Update" | Suraj | Done
|  | 2 | Add last column, after Approve, Called "Decline". I like the update of are you sure. This will apply after all boxes are selected by user. | Suraj | Done |  |  | Still needs the check box section in the actual row.
|  | 3 | Show the amount of request to be greater that Total Inventory remaining and/or greater than per bond limit amount | Suraj | Done
| AGENCIES / regulate | 1 | If Surety clicks on ACTIVE to SUSPEND the agency, besides reason, also prompt if State suspension or County Suspension. If County allow Surety user to enter multiple counties. | Suraj | Done
|  | 2 | Do not pre-populate the search and serach result. Lets aloow an input in the search and then bring up the data. 08/22/17 Please create a scenario where we can type in a License # and have the data populate as if we found the record in the system. Lets use License # "123456". | Suraj | Done
| AGENT / regulate | 1 | If Surety clicks on ACTIVE to SUSPEND the agent, besides reason, also prompt if State suspension or County Suspension. If County allow Surety user to enter multiple counties. | Suraj | Done
|  | 2 | Do not pre-populate the search and serach result. Lets aloow an input in the search and then bring up the data. 08/22/17 Please create a scenario where we can type in a License # and have the data populate as if we found the record in the system. Lets use License # "123456". | Suraj | Done
| BONDS | 1 | The bonds showing in table; Bond Status is either "Posted", "Filed", "Forfeited", 'SJU", "Exhonerated" or "SJP" | Suraj | Done
|  | 2 | When click on one of the bonds (specific line item), the detail shows agency details. This section must show additional bond information (not agency). Additional detail bond information to show is: Indemnitor Name, Indemnitor Address, Indemnitor Date of birth, Indemnitor Social Security, Indemnitor Phone, Collateral Recived (will be either Y or N), Collateral Description, Court Address (full address), then Next Court Date. Below this show court date history | Suraj | Done
| BONDS / marks bond paid | 1 | Change DOI Zip to "Agency ZIP Code" | Suraj | Done
|  | 2 | Change Bond County to Agency County | Suraj | Done
|  | 3 | Initially show the checkboxes unchecked | Suraj | Done
| All | 1 | There are many tables within the Surity UI's including the drill down levels that show "Surety" in the column heading when it is Agency" . Example: Click on HOME / Liabilities and the 1st 2 column headings say "surety" and it should be 'Agency". Also if you drill down on one the those rows agian it shows 'Surety" in the column heading and it should be 'Agency" | Suraj | Done
| Agency & Agent Regulate | 1 | When you click on the Status "ACTIVE" I like how you have the pop up with radio buttons to SUSPEND by State or County. However, when you clcik on county I also like the popo up to allow user to choose a county but the user may chose more than one county. Perhapsyou could have another box to show each county selected. The user may need to click on 2 or more counties. Even if the user ony clicks on 1 county show the choses county in another box (again this will show well if the user selects more than 1 county). | Suraj | Done
| ALL screens showing STATUS | 1 | Allow user to click on status anywhere in the system and allow them to change the status on the fly. Going from SUSPENDED to ACTIVE is easier but if the status is ACTIVE and the user clciks on ACTIVE present the same behavior as the action item in the prior item of Agency & Agent Regulate. IMPORTANT: A Surety can only change the Surety Status not a DOI status. Same that a DOI user can only change a DOI Status not a Surety Status. 9/25/17 From Home screen when cliking on one of the Info graphics like LIABILITIES" make sure you have a row that has the current STATUS = "ACTIVE" so we can test Suspending an entiry from anywhere in the system. | Suraj | Done |  |  | Make sure all screens, including screens at lower levels that show status allow for a STATUS CHANGE.
| Suspention History List | 1 | Whenever you show the Suspention history, change title of 1st column from 'Date Suspended" to "Disposition Date"; then insert a 2nd column titled "Governing Entity". The Governing Entiry could be "Surety" or "DOI". | Suraj | Done |  |  | Note: The Suspention History may need to be changed to "Suspention/Active History" since a record for any status change (ACTIVE to SUSPENDED or SUSPENDED to ACTIVE) is written to this file.

## Don Notes only
Don's notes only
On top 5 agencies and agents in forfeiture from Surety homer page allow user to click number of weeks. Currently show only 4 weeks
DO we add Owner Name as part of the Agency initial information. "Contact" may be the best way. This could be the owner or a President who is not necessarily the owner.
If court date is missed a message goes to Agent, Agency and Surety
Jeff suggested, dor DOI, to go to DOI site and see how things are listed