## Sheet1
Validify UI Screen Status
Entity | Screen | Action Item# | Action Item Description | Responsible | Status | Due Date | Completed Date
All | Login | 1 | Provide Suraj with new tempory logo (provided by Adam) | Don | Done | 2017-07-29 | 2017-07-29
|  | 2 | Insert new temporary logo | Suraj | Open
|  | 3 | Remove "Contact" and phone number from bottom of page | Suraj | Open
|  | 4 | Add 'Validify all rights reserved" at bottom of page | Suraj | Open
|  | 5 | Provide public search UI behavior for log in page area | Don | Open
|  | 6 | Split into 2 sections. 1 The nomral Validify user login. 2 A section for public record search (Don to provide functionlaity) | Suraj | Open
| All | 1 | Remove Validify from top left of UI's (remove Validify branding on all pages except login) | Suraj | Open
|  | 2 | Make Left menu column go all the way to top of page | Suraj | Open
|  | 3 | Move the 3 dash lines to the far left just above the side menu icons | Suraj | Open
|  | 4 | Have Search box at top right of all UI's. Also have the word 'Search" within the seach box. As user begins typing in the search box start showing all matches in a pop up box below that matches regardless of Entity. From there the user can click on the specific item from a the pop up. | Suraj | Open
|  | 5 | Any UI that displays a table/detail listing of data, highlite the column that is being sorted | Sura | Open
|  | 6 | Anywhere a status is shown add "Since" in the column header. Since represents the date the status occurred. Always show the word 'ACTIVE" in green and "SUSPENDED" in red. In the colummn details show the status and directly below the stats show the date that status occured.
|  | 7 | Provide UI behavior for data in pop up screen resulting from upper left search box for all screens | Don | Open
DOI | Home Page | 1 | Remove graphics from pods | Suraj | Open
|  | 2 | Simplify verbage in the top 3 pods to: "Liabilities", Forfeitures" & "Unpaid Judgements" | Suraj | Open
|  | 3 | Round the $ in the top 3 pods; ex: 5.2B or 1.2M or 2.3k | Suraj | Open
|  | 4 | On Top 3 Pods change "Number of Bonds" to '# Bonds" | Surja | Open
|  | 5 | Consolidate the bottom 3 Suspension pods into 1 pod (make it the 4th pod across the page). Once use clicks on this pod display 4 buttons : "Surreties" "Agencies" "Agents" and "All". Show the cooresponding list table depending on which entiry selected. If user selects all the show all the tables in the bottom area of the screen. | Suraj | Open
| Home Page / Liabilities | 1 | When click on Liabilities, must prompt for which entity Liabilities to be shown: 'Sureties" Agencies" or "Agents" | Suraj | Open
|  | 2 | Once you choose which entity ttype hen show the selected entity type in the first 2 columns not all three. Only show one of the entiy types "Sureties", "Agencies" or "Agents". | Suraj | Open
| Home Page / Forfeitures | 1 | When click on Forfeitures, must prompt for which entity Liabilities to be shown: 'Sureties" Agencies" or "Agents" | Suraj | Open
|  | 2 | Once you choose which entity ttype hen show the selected entity type in the first 2 columns not all three. Only show one of the entiy types "Sureties", "Agencies" or "Agents". | Suraj | Open
| Home Page / Judgements Unpaid | 1 | When click on Judgements Unpaid, must prompt for which entity Liabilities to be shown: 'Sureties" Agencies" or "Agents" | Suraj | Open
|  | 2 | Once you choose which entity ttype hen show the selected entity type in the first 2 columns not all three. Only show one of the entiy types "Sureties", "Agencies" or "Agents". | Suraj | Open